## ww23p5_supreetha
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.04 | 0.76 | 50 | WW24p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.042 | -15.86 | 1230 | -0.018 | -1.6 | 200 | -0.042 | -2.43 | 176 | -0.031 | -0.454 | 51 | 68.32 | 0.21 | 35 | WW24p2 | avpar4 fixes IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/ww19p4_coll_avpar2/builds/smavpar2.ww19def_exp12
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | -0.125 | -18.5 | 192 | -0.123 | -18.16 | 192 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.011 | -0.073 | 15 | 0 | 0 | 0 | -0.05 | -0.091 | 2 | -0.105 | -0.105 | 1 | 74 | 0.19 | 16 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons_updt/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.515 | -0.715 | 2 | -0.515 | -0.515 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.00629 | -0.02 | 16 |  |  |  | -0.10374 | -1 | 13 |  |  |  | 69.7948 | 0.1721% | 30 | ww24p4 | ISO in channel or ISO beneath the macros? Diodes to be removed? Other viols with vdencpar1(visa) and vdencpar5 (net fixes) need to be checked | Run with inter fixes started
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.029 | -0.214 | 44 | -0.012 | -0.061 | 6 | -0.133 | 0.141 | 2 | -0.133 | 0.141 | 2 | 64.19 | 0.19 | 2 | ww24p2 | wns path - vdenc2 will do fixes; hcp3 EP - s2n is -20ps
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.072 | -0.486 | 17 | -0.072 | -0.173 | 5 | 75.24 | 0.31 | 53 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.206 | -0.316 | 2 | -0.203 | -0.203 | 1 | 68.8 | 0.18 | 41 | WW23p1
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | -0.044 | -0.044 | 1 | -0.044 | -0.044 | 1 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.03904 | -0.03904 | 1 | -0.038984 | -0.038984 | 1 | 76.97 | 0.15 | 22 | ww24p1 | n-1 db looking clean interms of all inter with s2n so freezing it |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/
20 | smsfc | Praveen | -0.054 | -5.5 | 523 | -0.054 | -2.25 | 233 | -0.097 | -0.206 | 3 | -0.097 | -0.205 | 3 | 71.36 | 0.065 | 127 | WW24 | N-1 : Intra - 24ps/85 with S2N ; Inter - clean ; shorts : 78 | add buffer on route trying one trial exp | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_guide_script_ww20p6
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 |  |  |  | -0.224 | -0.47 | 5 |  |  |  | 65.82 | 0.1 | 9 | WW23p5 | 1 path with vdencpar2, buffering issue, s2n? |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.interrun/
23 | smveboxpar1 | Bhargav | -0.059 | -3.07 | 239 | -0.044 | -0.629 | 41 | -0.106 | -2.67 | 65 | -0.103 | -1.098 | 22 | 71.78 | 0.22 | 51 | WW24p1 | final runs to be started today |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_21/pbharg2x/WW18P5/builds/smveboxpar1.WW22p2_newdefKO_withinterfixes90_sbclkappliedforport/
24 | smveboxpar2 | Praveen | -0.04 | -1.42 | 553 | -0.042 | -0.831 | 62 | 0 | 0 | 0 | -0.132 | -0.132 | 1 | 75.3 | 0.12 | 97 |  | Only short fixes is pending |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_22/updated_1p0def/builds/smveboxpar2.ww19def_exp19
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_25/SD1p0_19p4/builds/scmi_xetlb.WW22p2_bestrun_withallinterfixes
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.17 | -30.84 | 34 | -2.17 | -30.84 | 34 | 76.2 | 0.3 | 53 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0/builds/sminf.ll/10_pre_cts/510_trial_route_opt/work/sminf.ndm/
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 |  | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.009 | -0.021 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | 1.1 | 127 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_15/bankgtnewdef115/builds/sqbankgt.newdef115appoption/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -1.1 | -4.98 | 9 | -1.1 | -4.98 | 9 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0.737 | 6 | WW24 | All buffering issues are fixed manually, SPV IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.164 | 9 | -0.029 |  |  | 65.96 | 0.49 | 42 |  | we have repeater viols, but startpoint have met with 316 ps margin in SPV, the repeater bound needed in sqidigt | To fix 115 shorts, started 3 runs, 1. with branching TRO by applying search n repair script, 2. by removing the KOM to one hierarchy, 3. by reducing KOM from 0.1 to 0.05
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.053 | -0.953 | 47 | -0.047 | -0.823 | 44 | 64.22 | 0.64 | 39 | WW24 | 53ps - sqidigt to tighten tcon; 31ps - s2n is 16ps |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p1_bestdb+interfixes_maxdelay250/

## ww23p5
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.04 | 0.76 | 50 | WW24p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.042 | -15.86 | 1230 | -0.018 | -1.6 | 200 | -0.042 | -2.43 | 176 | -0.031 | -0.454 | 51 | 68.32 | 0.21 | 35 | WW24p2 | intra clean in SWAP2NOM
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | -0.125 | -18.5 | 192 | -0.123 | -18.16 | 192 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.011 | -0.073 | 15 | 0 | 0 | 0 | -0.05 | -0.091 | 2 | -0.105 | -0.105 | 1 | 74 | 0.19 | 16 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons_updt/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.515 | -0.715 | 2 | -0.515 | -0.515 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.00629 | -0.02 | 16 | 0 | 0 | 0 | -0.178 | -1.17 | 14 | -0.178 | -1.156 | 14 | 69.7948 | 0.17 | 30 | ww24p4 | There are some vioalting paths where the timing paths are between a port and physical only cell (full_name:diode; ref_name:TIE) | Run with inter fixes started
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.029 | -0.214 | 44 | -0.012 | -0.061 | 6 | -0.133 | 0.141 | 2 | -0.133 | 0.141 | 2 | 64.19 | 0.19 | 2 | WW23p4
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/blalitex.sdp1/blalitex.ww19p3/builds/smhcppar1.KO_ww20p5_TRO_BRANCH/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm/
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.072 | -0.486 | 17 | -0.072 | -0.173 | 5 | 75.24 | 0.31 | 53 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.206 | -0.316 | 2 | -0.203 | -0.203 | 1 | 68.8 | 0.18 | 41 | WW23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | -0.044 | -0.044 | 1 | -0.044 | -0.044 | 1 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.03904 | -0.03904 | 1 | -0.038984 | -0.038984 | 1 | 76.97 | 0.15 | 22 | ww23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm
20 | smsfc | Praveen | -0.054 | -5.5 | 523 | -0.054 | -2.25 | 233 | -0.097 | -0.206 | 3 | -0.097 | -0.205 | 3 | 71.36 | 0.065 | 78 | WW24 | Path group started for Intra Viols along with Inter fixes constraints | add buffer on route trying one trial exp
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 |  |  |  | -0.224 | -0.47 | 5 |  |  |  | 65.82 | 0.1 | 9 | WW23p5 | Path group started for Intra Viols along with Inter fixes constraints for hcppar1
23 | smveboxpar1 | Bhargav | -0.059 | -3.07 | 239 | -0.044 | -0.629 | 41 | -0.106 | -2.67 | 65 | -0.103 | -1.098 | 22 | 71.78 | 0.22 | 51 | WW24p1 | Run started with inter fixes along with intra timing fixes is in progress
24 | smveboxpar2 | Praveen | -0.04 | -1.9 | 102 | -0.032 | -0.438 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 75.3 | 0.12 | 97 | WW24p3 | 1.inter fixes for sfc and decip are added 2. intra timing updated wrt partition level
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.17 | -30.84 | 34 | -2.17 | -30.84 | 34 | 76.2 | 0.3 | 53 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0/builds/sminf.ll/10_pre_cts/510_trial_route_opt/work/sminf.ndm/
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 |  | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.009 | -0.021 | 11 | 0 | 0 | 0 | -0.80225 | -2.9878 | 12 |  |  |  | 72 | 1.1 | 156 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_15/bankgtnewdef115/builds/sqbankgt.newdef115appoption/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -1.1 | -4.98 | 9 | -1.1 | -4.98 | 9 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0.737 | 6 | WW24 | Have applied tcons for all FT Violations.
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.164 | 9 | -0.029 |  |  | 65.96 | 0.49 | 42 |  | we have repeater viols, but startpoint have met with 316 ps margin in SPV, the repeater bound needed in sqidigt | To fix 115 shorts, started 3 runs, 1. with branching TRO by applying search n repair script, 2. by removing the KOM to one hierarchy, 3. by reducing KOM from 0.1 to 0.05 | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for inter violations net length is more in sag_xetlb. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.053 | -0.953 | 47 | -0.047 | -0.823 | 44 | 64.22 | 0.64 | 39 | WW24 | sag inter viols |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm

## ww24p1
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.04 | 0.76 | 50 | WW24p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.042 | -15.86 | 1230 | -0.018 | -1.6 | 200 | -0.042 | -2.43 | 176 | -0.031 | -0.454 | 51 | 68.32 | 0.21 | 35 | WW24p2 | avpar4 viols fixed, 1 intra at 120ps |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/ww19p4_coll_avpar2/builds/smavpar2.ww19def_exp12
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | -0.125 | -18.5 | 192 | -0.123 | -18.16 | 192 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.011 | -0.073 | 15 | 0 | 0 | 0 | -0.05 | -0.091 | 2 | -0.105 | -0.105 | 1 | 74 | 0.19 | 16 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons_updt/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.515 | -0.715 | 2 | -0.515 | -0.515 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.00629 | -0.02 | 16 |  |  |  | -0.10374 | -1 | 13 |  |  |  | 69.7948 | 0.1721% | 30 | ww24p4 | top violators - fixes in vdencpar5; next violation - check for S2N | Run with inter fixes started
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.029 | -0.214 | 44 | -0.012 | -0.061 | 6 | -0.133 | 0.141 | 2 | -0.133 | 0.141 | 2 | 64.19 | 0.19 | 2 | ww24p6 | doing fixes for inter
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/blalitex.sdp1/blalitex.ww19p3/builds/smhcppar1.KO_ww20p5_TRO_BRANCH/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm/
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.072 | -0.486 | 17 | -0.072 | -0.173 | 5 | 75.24 | 0.31 | 53 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.206 | -0.316 | 2 | -0.203 | -0.203 | 1 | 68.8 | 0.18 | 41 | WW23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | -0.044 | -0.044 | 1 | -0.044 | -0.044 | 1 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.03904 | -0.03904 | 1 | -0.038984 | -0.038984 | 1 | 76.97 | 0.15 | 22 | ww24p1 | n-1 db looking clean interms of all inter with s2n so freezing it |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm/
20 | smsfc | Praveen | -0.059 | -2.7 | 403 | -0.048 | -1.7 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 71.36 | 0.065 | 38 | WW24 | waiting for s2n reports | add buffer on route trying one trial exp | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_guide_script_ww20p6
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 65.82 | 0.1 | 9 | WW23p5 | 1 path with vdencpar2, buffering issue, s2n? |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.interrun/
23 | smveboxpar1 | Bhargav | -0.059 | -3.07 | 239 | -0.044 | -0.629 | 41 | -0.106 | -2.67 | 65 | -0.103 | -1.098 | 22 | 71.78 | 0.22 | 51 | WW24p1 | final runs to be started today |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_21/pbharg2x/WW18P5/builds/smveboxpar1.WW22p2_newdefKO_withinterfixes90_sbclkappliedforport/
24 | smveboxpar2 | Praveen | -0.04 | -1.42 | 553 | -0.042 | -0.831 | 62 | 0 | 0 | 0 | -0.132 | -0.132 | 1 | 75.3 | 0.12 | 90 |  | Only short fixes is pending - to check s2n inter |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_22/updated_1p0def/builds/smveboxpar2.ww19def_exp19
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_25/SD1p0_19p4/builds/scmi_xetlb.WW22p2_bestrun_withallinterfixes
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.17 | -30.84 | 34 | -2.17 | -30.84 | 34 | 76.2 | 0.3 | 53 | WW27 | convereged with 14p6 RTL, waiting for SPV |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0/builds/sminf.ll/10_pre_cts/510_trial_route_opt/work/sminf.ndm/
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 | 4K | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.009 | -0.021 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.1 | 2 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/newdef205/builds/sqbankgt.congestionefforthigh/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -1.1 | -4.98 | 9 | -1.1 | -4.98 | 9 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0.737 | 6 | WW24 | SPV to be checked |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.164 | 9 | -0.029 |  |  | 65.96 | 0.49 | 42 |  | we have repeater viols, but startpoint have met with 316 ps margin in SPV, the repeater bound needed in sqidigt | To fix 115 shorts, started 3 runs, 1. with branching TRO by applying search n repair script, 2. by removing the KOM to one hierarchy, 3. by reducing KOM from 0.1 to 0.05 | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.053 | -0.953 | 47 | -0.047 | -0.823 | 44 | 64.22 | 0.64 | 39 | WW24 | 53ps - sqidigt to tighten tcon; 31ps - s2n is 16ps |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm

## ww24p2
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | -0.079 | -0.079 | 1 | -0.079 | -0.079 | 1 | 61.04 | 0.76 | 50 | WW24p2 | inter S2N WNS -0.032/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.133 | -29.8 | 1999 | -0.133 | -2.79 | 278 | -0.049 | -2.41 | 178 | -0.029 | -0.516 | 60 | 68.38 | 0.22 | 30 | WW24p2 | intra S2N WNS -0.01/1 inter S2N -0.032/67 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/www19defexpts/builds/smavpar2.ww19def_interfixespar1_par4/10_pre_cts/510_trial_route_opt/work/smavpar2.ndm
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.008 | -0.061 | 21 | 0 | 0 | 0 | -0.058 | -0.072 | 3 | -0.057 | -0.058 | 2 | 74.13 | 0.19 | 19 |  | inter S2N WNS -0.034/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.062 | -0.062 | 1 | -0.06 | -0.06 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.004 | -0.02 | 20 | 0 | 0 | 0 | -0.118 | -0.159 | 6 | -0.118 | -0.159 | 6 | 69.79 | 0.17 | 30 | ww24p4 | to start an SPV with latest veboxpar1, we are seeing 180ps/80ps improvement in TRO | Run with inter fixes started
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.006 | -0.015 | 5 | 0 | 0 | 0 | -0.063 | -8.91 | 449 | -0.058 | -8.71 | 435 | 64.16 | 0.2 | 4 | ww24p6 | vdencpar5, interactive fixes for one viols
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/lynx/models/LNL_SD1p0_ww14p6/builds/smhcppar1.KO_ww20p5_script_TRO/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.078 | -0.228 | 6 | -0.078 | -0.21 | 4 | 75.24 | 0.31 | 53 | WW23p3 | inter S2N WNS -0.052/4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.085 | -0.085 | 1 | -0.085 | -0.085 | 1 | 68.8 | 0.18 | 41 | WW23p1 | inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.177 | -0.177 | 1 | -0.171 | -0.171 | 1 | 76.97 | 0.15 | 22 | ww24p1 | intra S2N WNS -0.028/2 inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm/
20 | smsfc | Praveen | -0.059 | -2.7 | 403 | -0.048 | -1.7 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 71.36 | 0.065 | 38 | WW24 | intra S2N WNS -0.001/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_grppath_rgm1m2_ww23p4/10_pre_cts/510_trial_route_opt/work/smsfc.ndm
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 | -0.014 | -0.014 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 65.82 | 0.1 | 9 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.inter/10_pre_cts/510_trial_route_opt/work/smvdboxtop.ndm
23 | smveboxpar1 | Bhargav | -0.038 | -1.04 | 120 | -0.018 | -0.136 | 18 | -0.136 | -2.502 | 63 | -0.131 | -1.08 | 22 | 71.86 | 0.22 | 38 | WW24p1 | to start an SPV with latest veboxpar1, we are seeing 50ps improvement in TRO
24 | smveboxpar2 | Praveen | -0.04 | -1.42 | 553 | -0.042 | -0.831 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 75.3 | 0.12 | 97 |  | veboxpar2 39 shorts db, can be used for SPV with all other latets pars
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | -0.004 | -0.005 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.21 | -33.96 | 45 | -2.21 | -33.96 | 45 | 76.2 | 0.29 | 53 | WW27 | tapclk issue |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0Lt/builds/sminf.fullfix/10_pre_cts/510_trial_route_opt/work/sminf.ndm
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 | 4K | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.01 | -0.019 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0.94 | 2 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/newdef205/builds/sqbankgt.congestionefforthigh/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -0.295 | -1.02 | 8 | -0.295 | -1.02 | 8 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.9 | 0.74 | 2 | WW24 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc_ftcon/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.151 | 8 | -0.029 | -0.133 | 8 | 65.96 | 0.49 | 42 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.045 | -0.52 | 29 | -0.044 | -0.395 | 27 | 64.22 | 0.64 | 39 | WW24 | intra S2N clean inter S2N WNS -0.027/5 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm

## ww24p4
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | -0.079 | -0.079 | 1 | -0.079 | -0.079 | 1 | 61.04 | 0.76 | 50 | WW24p2 | inter S2N WNS -0.032/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.133 | -29.8 | 1999 | -0.133 | -2.79 | 278 | -0.049 | -2.41 | 178 | -0.029 | -0.516 | 60 | 68.38 | 0.22 | 30 | WW24p2 | intra S2N WNS -0.01/1 inter S2N -0.032/67 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/www19defexpts/builds/smavpar2.ww19def_interfixespar1_par4/10_pre_cts/510_trial_route_opt/work/smavpar2.ndm
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.008 | -0.061 | 21 | 0 | 0 | 0 | -0.058 | -0.072 | 3 | -0.057 | -0.058 | 2 | 74.13 | 0.19 | 19 |  | inter S2N WNS -0.034/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.062 | -0.062 | 1 | -0.06 | -0.06 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.004 | -0.02 | 20 | 0 | 0 | 0 | -0.118 | -0.159 | 6 | -0.118 | -0.159 | 6 | 69.79 | 0.17 | 30 | ww24p4 | to start an SPV with latest veboxpar1, we are seeing 180ps/80ps improvement in TRO Eco fixes, implemented, but due to tool crash, the results not yet out. One inter viols is pending at WNS -54ps in swap2nom | Run with inter fixes started
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.006 | -0.015 | 5 | 0 | 0 | 0 | -0.063 | -8.91 | 449 | -0.058 | -8.71 | 435 | 64.16 | 0.2 | 4 | ww24p6 | vdencpar5, interactive fixes for one viols ECO fixes worked on n-1 viols, new viols came now due to net detouring.
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/lynx/models/LNL_SD1p0_ww14p6/builds/smhcppar1.KO_ww20p5_script_TRO/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.078 | -0.228 | 6 | -0.078 | -0.21 | 4 | 75.24 | 0.31 | 53 | WW23p3 | inter S2N WNS -0.052/4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.085 | -0.085 | 1 | -0.085 | -0.085 | 1 | 68.8 | 0.18 | 41 | WW23p1 | inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.177 | -0.177 | 1 | -0.171 | -0.171 | 1 | 76.97 | 0.15 | 22 | ww24p1 | intra S2N WNS -0.028/2 inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm/
20 | smsfc | Praveen | -0.059 | -2.7 | 403 | -0.048 | -1.7 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 71.36 | 0.065 | 38 | WW24 | intra S2N WNS -0.001/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_grppath_rgm1m2_ww23p4/10_pre_cts/510_trial_route_opt/work/smsfc.ndm
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 | -0.014 | -0.014 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 65.82 | 0.1 | 9 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.inter/10_pre_cts/510_trial_route_opt/work/smvdboxtop.ndm
23 | smveboxpar1 | Bhargav | -0.038 | -1.04 | 120 | -0.018 | -0.136 | 18 | -0.136 | -2.502 | 63 | -0.131 | -1.08 | 22 | 71.86 | 0.22 | 38 | WW24p1 | to start an SPV with latest veboxpar1, we are seeing 50ps improvement in TRO, waiting for TRO db, delayed due to subtask rerun.
24 | smveboxpar2 | Praveen | -0.04 | -6.49 | 492 | -0.033 | -1.32 | 97 | -0.168 | -0.168 | 1 | -0.168 | -0.168 | 1 | 75.44 | 0.11 | 39 |  | veboxpar2 39 shorts db, can be used for SPV with all other latets pars inter viols will be clean in S2N. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_22/updated_1p0def/builds/smveboxpar2.ww19def_exp12/10_pre_cts/510_trial_route_opt/work/smveboxpar2.ndm
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | -0.004 | -0.005 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_25/SD1p0_19p4/builds/scmi_xetlb.WW22p2_bestrun_withallinterfixes/10_pre_cts/510_trial_route_opt/work/scmi_xetlb.ndm
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.21 | -33.96 | 45 | -2.21 | -33.96 | 45 | 76.2 | 0.29 | 53 | WW27 | tapclk issue |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0Lt/builds/sminf.fullfix/10_pre_cts/510_trial_route_opt/work/sminf.ndm
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 | 4K | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.01 | -0.019 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0.94 | 2 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/newdef205/builds/sqbankgt.congestionefforthigh/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -0.295 | -1.02 | 8 | -0.295 | -1.02 | 8 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.9 | 0.74 | 2 | WW24 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc_ftcon/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.151 | 8 | -0.029 | -0.133 | 8 | 65.96 | 0.49 | 42 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.045 | -0.52 | 29 | -0.044 | -0.395 | 27 | 64.22 | 0.64 | 39 | WW24 | intra S2N clean inter S2N WNS -0.027/5 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm

## ww24p5
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | -0.079 | -0.079 | 1 | -0.079 | -0.079 | 1 | 61.04 | 0.76 | 50 | WW24p2 | inter S2N WNS -0.032/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.133 | -29.8 | 1999 | -0.133 | -2.79 | 278 | -0.049 | -2.41 | 178 | -0.029 | -0.516 | 60 | 68.38 | 0.22 | 30 | WW24p2 | intra S2N WNS -0.01/1 inter S2N -0.032/67 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/www19defexpts/builds/smavpar2.ww19def_interfixespar1_par4/10_pre_cts/510_trial_route_opt/work/smavpar2.ndm
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.008 | -0.061 | 21 | 0 | 0 | 0 | -0.058 | -0.072 | 3 | -0.057 | -0.058 | 2 | 74.13 | 0.19 | 19 |  | inter S2N WNS -0.034/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.062 | -0.062 | 1 | -0.06 | -0.06 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.004 | -0.02 | 20 | 0 | 0 | 0 | -0.118 | -0.159 | 6 | -0.118 | -0.159 | 6 | 69.79 | 0.17 | 30 | ww24p4 | to start an SPV with latest veboxpar1, we are seeing 180ps/80ps improvement in TRO Eco fixes, implemented, but due to tool crash, the results not yet out. One inter viols is pending at WNS -54ps in swap2nom | Run with inter fixes started | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/vdencpar21p0/builds/smvdencpar2.isolationECO/10_pre_cts/510_trial_route_opt/work/smvdencpar2.ndm
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.006 | -0.015 | 5 | 0 | 0 | 0 | -0.063 | -8.91 | 449 | -0.058 | -8.71 | 435 | 64.16 | 0.2 | 4 | ww24p6 | vdencpar5, interactive fixes for one viols ECO fixes worked on n-1 viols, new viols came now due to net detouring. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/dencpar5/builds/smvdencpar5.final_relay_fix/10_pre_cts/510_trial_route_opt/work/smvdencpar5.ndm
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/lynx/models/LNL_SD1p0_ww14p6/builds/smhcppar1.KO_ww20p5_script_TRO/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.078 | -0.228 | 6 | -0.078 | -0.21 | 4 | 75.24 | 0.31 | 53 | WW23p3 | inter S2N WNS -0.052/4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.085 | -0.085 | 1 | -0.085 | -0.085 | 1 | 68.8 | 0.18 | 41 | WW23p1 | inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.177 | -0.177 | 1 | -0.171 | -0.171 | 1 | 76.97 | 0.15 | 22 | ww24p1 | intra S2N WNS -0.028/2 inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm/
20 | smsfc | Praveen | -0.059 | -2.7 | 403 | -0.048 | -1.7 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 71.36 | 0.065 | 38 | WW24 | intra S2N WNS -0.001/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_grppath_rgm1m2_ww23p4/10_pre_cts/510_trial_route_opt/work/smsfc.ndm
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 | -0.014 | -0.014 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 65.82 | 0.1 | 9 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.inter/10_pre_cts/510_trial_route_opt/work/smvdboxtop.ndm
23 | smveboxpar1 | Bhargav | -0.038 | -1.04 | 120 | -0.018 | -0.136 | 18 | -0.136 | -2.502 | 63 | -0.131 | -1.08 | 22 | 71.86 | 0.22 | 38 | WW24p1 | to start an SPV with latest veboxpar1, we are seeing 50ps improvement in TRO, waiting for TRO db, delayed due to subtask rerun.
24 | smveboxpar2 | Praveen | -0.04 | -6.49 | 492 | -0.033 | -1.32 | 97 | -0.168 | -0.168 | 1 | -0.168 | -0.168 | 1 | 75.44 | 0.11 | 39 |  | veboxpar2 39 shorts db, can be used for SPV with all other latets pars inter viols will be clean in S2N. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_22/updated_1p0def/builds/smveboxpar2.ww19def_exp12/10_pre_cts/510_trial_route_opt/work/smveboxpar2.ndm
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | -0.004 | -0.005 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_25/SD1p0_19p4/builds/scmi_xetlb.WW22p2_bestrun_withallinterfixes/10_pre_cts/510_trial_route_opt/work/scmi_xetlb.ndm
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.21 | -33.96 | 45 | -2.21 | -33.96 | 45 | 76.2 | 0.29 | 53 | WW27 | tapclk issue |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0Lt/builds/sminf.fullfix/10_pre_cts/510_trial_route_opt/work/sminf.ndm
27 | smsqidigt | Praveen | -0.005 | -0.007 | 2 | [10 empty] | 0.57 | 4K | WW27 | TRO IP
28 | sqbankgt | Nisant | -0.01 | -0.019 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0.94 | 2 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/newdef205/builds/sqbankgt.congestionefforthigh/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -0.295 | -1.02 | 8 | -0.295 | -1.02 | 8 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.9 | 0.74 | 2 | WW24 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc_ftcon/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.151 | 8 | -0.029 | -0.133 | 8 | 65.96 | 0.49 | 42 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.045 | -0.52 | 29 | -0.044 | -0.395 | 27 | 64.22 | 0.64 | 39 | WW24 | intra S2N clean inter S2N WNS -0.027/5 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm

## ww24p7
S.No | Partition | Leads | Intra viols (SPV) |  |  | Intra viols (PBA) |  |  | Inter viols (SPV) |  |  | Inter viols (PBA) |  |  | Util % (TRO) | Congestion (preCTS) | Shorts (TRO) | ETA | Comments | Plan of Action | DB Pointer
|  |  | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP | WNS | TNS | NVP
1 | smavpar1 | Nisant | -0.005 | -0.103 | 49 | 0 | 0 | 0 | -0.079 | -0.079 | 1 | -0.079 | -0.079 | 1 | 61.04 | 0.76 | 50 | WW24p2 | inter S2N WNS -0.032/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_10/smavpar1_1p0_new/builds/smavpar1.branch_tro_133_rg/10_pre_cts/510_trial_route_opt/work/smavpar1.ndm
2 | smavpar2 | Praveen | -0.133 | -29.8 | 1999 | -0.133 | -2.79 | 278 | -0.049 | -2.41 | 178 | -0.029 | -0.516 | 60 | 68.38 | 0.22 | 30 | WW24p2 | intra S2N WNS -0.01/1 inter S2N -0.032/67 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_06/www19defexpts/builds/smavpar2.ww19def_interfixespar1_par4/10_pre_cts/510_trial_route_opt/work/smavpar2.ndm
3 | smavpar3 |  | -0.005 | -0.016 | 21 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.81 | 0.15 | 19 |  |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_07/refreshpoint1/builds/smavpar3.boundandinter/10_pre_cts/510_trial_route_opt/work/smavpar3.ndm/
4 | smavpar4 | Venkatesh | -0.008 | -0.04 | 16 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 61.99 | 0.24 | 8 | WW23p3 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_08/sbikkinx/sd1p0_ww19/builds/smavpar4.sd1p0_ww19_inter_fix/10_pre_cts/510_trial_route_opt/work/smavpar4.ndm
5 | smavpar5 | Santhosh | -0.008 | -0.061 | 21 | 0 | 0 | 0 | -0.058 | -0.072 | 3 | -0.057 | -0.058 | 2 | 74.13 | 0.19 | 19 |  | inter S2N WNS -0.034/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_09/ww18p6_avpar5/builds/smavpar5.tcons/10_pre_cts/510_trial_route_opt/work/smavpar5.ndm
6 | smvdencpar1 | Santhosh | -0.002 | -0.008 | 7 | 0 | 0 | 0 | -0.062 | -0.062 | 1 | -0.06 | -0.06 | 1 | 73.54 | 0.39 | 4 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_14/lynx/models/LNL_SD1p0_ww14p6/builds/smvdencpar1.branchsnr80/10_pre_cts/510_trial_route_opt/work/smvdencpar1.ndm
7 | smvdencpar2 | Nisant | -0.002 | -0.012 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.7 | 0.186 | 29 | ww24p4 | to start an SPV with latest veboxpar1, we are seeing 180ps/80ps improvement in TRO Eco fixes, implemented, but due to tool crash, the results not yet out. One inter viols is pending at WNS -54ps in swap2nom | Run with inter fixes started | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/vdencpar21p0/builds/smvdencpar2.isolationECO/10_pre_cts/510_trial_route_opt/work/smvdencpar2.ndm
8 | smvdencpar3 |  | -0.006 | -0.048 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 0.3 | 53 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_16/sdhulehx/SD1p0_19p4/builds/smvdencpar3.WW19p5_run_exp2_short_app/10_pre_cts/510_trial_route_opt/work/smvdencpar3.ndm
9 | smvdencpar4 |  | -0.003 | -0.049 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7 | 0.22 | 55 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_17/blalitesx.sdp1/builds/smvdencpar4.KO_ww19p1/10_pre_cts/510_trial_route_opt/work/smvdencpar4.ndm
10 | smvdencpar5 | Praveen | -0.019 | -0.165 | 49 | -0.005 | -0.005 | 1 | -0.053 | -0.053 | 1 | -0.053 | -0.053 | 1 | 64.16 | 0.21 | 3 | ww24p6 | vdencpar5, interactive fixes for one viols ECO fixes worked on n-1 viols, new viols came now due to net detouring. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/dencpar5/builds/smvdencpar5.final_relay_fix/10_pre_cts/510_trial_route_opt/work/smvdencpar5.ndm
11 | smhcppar1 | Bhargav | -0.029 | -0.944 | 116 | -0.003 | -0.003 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0.21 | 52 | ww23p5 | for inter violation i have started the run the run got completed prects and TRO IP |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_01/lynx/models/LNL_SD1p0_ww14p6/builds/smhcppar1.KO_ww20p5_script_TRO/10_pre_cts/510_trial_route_opt/work/smhcppar1.ndm
12 | smhcppar2 | Venkatesh | -0.019 | -0.064 | 15 | -0.004 | -0.004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 71.4 | 0.26 | 37 | ww21p4 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_02/srikanth/ww19_def/builds/smhcppar2.golden_run_short_fix/10_pre_cts/510_trial_route_opt/work/smhcppar2.ndm
13 | smhcppar3 | Venkatesh | -0.028 | -1.95 | 475 | -0.014 | -0.044 | 10 | -0.078 | -0.228 | 6 | -0.078 | -0.21 | 4 | 75.24 | 0.31 | 53 | WW23p3 | inter S2N WNS -0.052/4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_03/sbikkinx/sd1p0_ww19p4/builds/smhcppar3.sd1p0_ww19_ko_4_rd/10_pre_cts/510_trial_route_opt/work/smhcppar3.ndm
14 | smhcppar4 | Bhargav | -0.013 | -0.071 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.02 | 0.14 | 69 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_04/dnaveen2x/sd1p0/builds/smhcppar4.scripthigh/10_pre_cts/510_trial_route_opt/work/smhcppar4.ndm/
15 | smvvcpar1 | Nisant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.08 | 0.23 | 7 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_05/vvcpar1_1p0_new/builds/smvvcpar1.inter_345_tcon/10_pre_cts/510_trial_route_opt/work/smvvcpar1.ndm
16 | smvvcpar2 | Santhosh | -0.023 | -0.59 | 166 | -0.01 | -0.013 | 2 | -0.085 | -0.085 | 1 | -0.085 | -0.085 | 1 | 68.8 | 0.18 | 41 | WW23p1 | inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_11/jeasawrx/SD1p0/new_coll_WW18p6/builds/smvvcpar2.WW21p1_branch_shorts/10_pre_cts/510_trial_route_opt/work/smvvcpar2.ndm
17 | smvvcpar3 | Venkatesh | -0.001 | -0.006 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.38 | 0.22 | 64 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_12/venkatesh/sd1p0_ww18p6/builds/smvvcpar3.sd1p0_ww14p6_ortl_dupf_no_rp_blkgs_ovr_ebb_ww19p2_hier_km_ww19p5_inter_fix_ptgp/10_pre_cts/510_trial_route_opt/work/smvvcpar3.ndm
18 | smvvcpar4 | Nisant | -0.06 | -63 | 3439 | -0.052 | -1.77 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 47.06 | 0.21 | 2.1K |  | RTL not freezed
19 | smdecip | Bhargav | -0.051489 | -0.101 | 5 | -0.03185 | -0.102 | 4 | -0.177 | -0.177 | 1 | -0.171 | -0.171 | 1 | 76.97 | 0.15 | 22 | ww24p1 | intra S2N WNS -0.028/2 inter S2N clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_23/ww19p4_def_smdecip/amurug2x/builds/smdecip.sd1p0_ww19p4_def_Golden_57shorts_Newpathgrouptrail1_70iteration_tcon_bound_ww23p1/10_pre_cts/510_trial_route_opt/work/smdecip.ndm/
20 | smsfc | Praveen | -0.059 | -2.7 | 403 | -0.048 | -1.7 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 71.36 | 0.065 | 38 | WW24 | intra S2N WNS -0.001/1 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_24/sd1p0_9/builds/smsfc.sd1p0_ww19p4def_ebbreg_grppath_rgm1m2_ww23p4/10_pre_cts/510_trial_route_opt/work/smsfc.ndm
21 | smmfx |  | -0.007 | -0.023 | 11 | -0.002 | -0.002 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 75.5 | 0.2 | 57 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_19/ww18p6_smmfx_def/amurug2x/builds/smmfx.sd1p0_ww18p6_def_Golden_receipe_SNRLOOP_ww19p3/10_pre_cts/510_trial_route_opt/work/smmfx.ndm
22 | smvdboxtop | Santhosh | -0.015 | -0.015 | 1 | -0.014 | -0.014 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 65.82 | 0.1 | 9 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_20/po1/builds/smvdboxtop.inter/10_pre_cts/510_trial_route_opt/work/smvdboxtop.ndm
23 | smveboxpar1 | Bhargav | -0.037 | -1.86 | 173 | -0.021 | -0.213 | 27 | -0.092 | -1.618 | 57 | -0.09 | -0.766 | 21 | 72.01 | 0.22 | 41 | WW24p1 | after implementing the fix for top violators, the results are degraded. We are trying out the ECO fixes. For final db, we have -54ps/55 (27 are above -20ps) in swap2nom report | Manual ECO fixes in n-1 best db | /nfs/zsc3/disks/lnl_sip_a0_media_par_21/pbharg2x/WW18P5/builds/smveboxpar1.ww23p5_runwithrpdmovementwithallfixes_halfcycledelay/10_pre_cts/510_trial_route_opt/work/smveboxpar1.ndm
24 | smveboxpar2 | Praveen | -0.04 | -6.49 | 492 | -0.033 | -1.32 | 97 | -0.168 | -0.168 | 1 | -0.168 | -0.168 | 1 | 75.44 | 0.11 | 39 |  | veboxpar2 39 shorts db, can be used for SPV with all other latets pars inter viols will be clean in S2N. |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_22/updated_1p0def/builds/smveboxpar2.ww19def_exp12/10_pre_cts/510_trial_route_opt/work/smveboxpar2.ndm
25 | scmi_xetlb | Bhargav | -0.007 | -0.073 | 73 | -0.004 | -0.005 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7 | 0.13 | 7 | WW24p1 | Inter fixes run is running in TRO & ETA 23p4 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_25/SD1p0_19p4/builds/scmi_xetlb.WW22p2_bestrun_withallinterfixes/10_pre_cts/510_trial_route_opt/work/scmi_xetlb.ndm
26 | sminf | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | -2.21 | -33.96 | 45 | -2.21 | -33.96 | 45 | 76.2 | 0.29 | 53 | WW27 | tapclk issue |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_34/dnaveen2x/sd1p0Lt/builds/sminf.fullfix/10_pre_cts/510_trial_route_opt/work/sminf.ndm
27 | smsqidigt | Praveen | -0.066 | -4.64 | 470 | [9 empty] | 73.3 | 0.51 | 255 | WW27 | SPV is in progress
28 | sqbankgt | Nisant | -0.01 | -0.019 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0.94 | 2 | WW27 | convereged with 14p6 RTL |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_31/newdef205/builds/sqbankgt.congestionefforthigh/10_pre_cts/510_trial_route_opt/work/sqbankgt.ndm
29 | smsystem | Venkatesh | -0.008 | -0.037 | 12 | 0 | 0 | 0 | -0.295 | -1.02 | 8 | -0.295 | -1.02 | 8 | 70.3 | 0.14 | 6 | ww21p2 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_26/srikanth/1p0/builds/smsystem.1p0_golden_run_gp_new_hsd/10_pre_cts/510_trial_route_opt/work/smsystem.ndm
30 | smicxlpar1 | Santhosh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.9 | 0.74 | 2 | WW24 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_30/santhosh/ww21p5_icxl/builds/smicxlpar1.ww21p5_icxl_cc_rpd_tcons_abc_ftcon/10_pre_cts/510_trial_route_opt/work/smicxlpar1.ndm
31 | smibank0 | Nisant | -0.033 | -0.43 | 39 | -0.012 | -0.041 | 6 | -0.031 | -0.151 | 8 | -0.029 | -0.133 | 8 | 65.96 | 0.49 | 42 | WW23p5 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_29/lynx/models/LNL_SD1p0_ww14p6/builds/smibank0.ww18p5_inter_allfixes_spv1p0_koupdtww19p1_ww20p1_congrestruct_bank02bank0_ww22p2_regbound/10_pre_cts/510_trial_route_opt/work/smibank0.ndm/
32 | smimfpar1 | Praveen | -0.012 | -0.036 | 7 | -0.009 | -0.017 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.91 | 0.91 | 25 | WW27 | shorts improved from 156 to 25. for feed thru inter viols, sqidigt will apply tcons, EP viols are clean |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_28/lynx/models/LNL_SD1p0_pre_refresh_ww20/builds/smimfpar1.final/10_pre_cts/510_trial_route_opt/work/smimfpar1.ndm
33 | gscpar | Venkatesh | -0.024 | -0.064 | 3 | -0.013 | -0.028 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 73.52 | 0.08 | 10 | ww23p1 |  |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_33/venkatesh/sd1p0_ww20p3/builds/smgsc.sd1p0_ww14p6_ortl_ebb_blkgs_inter_fix_hfs_prt_clk_ww20p5_ww21p2/10_pre_cts/510_trial_route_opt/work/smgsc.ndm
34 | sag_xetlb | Bhargav | -0.014 | -0.056 | 14 | -0.007 | -0.017 | 3 | -0.045 | -0.52 | 29 | -0.044 | -0.395 | 27 | 64.22 | 0.64 | 39 | WW24 | intra S2N clean inter S2N WNS -0.027/5 |  | /nfs/zsc3/disks/lnl_sip_a0_media_par_27/pbharg2x/WW17P3def/builds/sag_xetlb.WW22p7_finalrun_bestreceipe/10_pre_cts/510_trial_route_opt/work/sag_xetlb.ndm